# VELVET ELVES

AI-First Transaction Management Platform

# PROJECT MILESTONES

## 22-Week Timeline

| Date Established | March 4, 2026 |
| --- | --- |
| Start Date | Week 1 (March 9, 2026) |
| End Date | Week 22 (August 2, 2026) |
| Budget | Under USD $40,000 (Fixed-Price) |
| Tech Stack | React ¦ FastAPI ¦ OpenAI GPT ¦ Supabase ¦ AWS EC2 |

# Milestone Summary

| Phase | Weeks | Focus Area | Duration |
| --- | --- | --- | --- |
| 1 | 1-3 | Discovery, Architecture & Foundation | 3 weeks |
| 2 | 4-8 | Core Transaction & Task Engine | 5 weeks |
| 3 | 9-13 | AI Wizard & Document Management | 5 weeks |
| 4 | 14-16 | Communication Engine & AI Email | 3 weeks |
| 5 | 17-19 | Dashboards, Payments & Profiles | 3 weeks |
| 6 | 20-21 | White-Label, Integrations & Ad Hooks | 2 weeks |
| 7 | 22 | Testing, Deployment & Launch | 1 week |

PROJECT MILESTONES (22-WEEK TIMELINE + AS-BUILT STATUS)

Last Updated: 2026-08-25 (as-built status from frontend/backend source)

Original End Date: Week 22 (2026-08-02 / 2026-08-09)

AWS ECS + CloudFront | Stripe | SendGrid

CURRENT STATUS — 2026-08-25

The original 22-week checkbox list below is kept as the historical plan.

Status of that plan in source code:

COMPLETE (or effectively complete in code):

1.1, 1.2, 1.3, 2.1, 2.2, 2.3, 2.4, 2.5 (spec), 3.1–3.4, 4.1–4.3,

5.2 (invoices + $49/deal wallet; commission payouts PARKED),

5.3 (settings/playbook), 6.1 (white-label + calendar + CRM hooks),

6.2 (advertise storefront + admin ads)

MOSTLY COMPLETE / still polishing:

5.1 FSBO workspace pages exist; operating depth still iterating

7.1 Testing & hardening (large suites + Chrome QA; Aime cutover on stage)

7.2 Production infra is live; client QA is on staging; handoff open

STILL HOOKS (not in MVP delivery):

Native mobile, generic IMAP/SMTP, AI Coach paid add-on, orphan accounts,

custom video, named CRM (Follow Up Boss), Active Listings nav,

commission payouts, Supabase RLS activation

Work shipped AFTER the original Week 22 list is recorded as PHASE 8 below

(platform admin, Help Center, marketing site, deal workspace, Aime/Needs You,

document templates, client/vendor portal redesigns).

Staging: https://app.stage.velvetelves.com

Prod hosts: app.velvetelves.com, api.prod.velvetelves.com, help.velvetelves.com

# Phase 1: Discovery, Architecture & Foundation

Weeks 1-3

## Milestone 1.1 - Project Setup & Architecture Design (Week 1)

STATUS: COMPLETE (2026-08-25)

Deliverables:

[ ] Review legacy ASP.NET MVC codebase and scope documents

[ ] Finalize system architecture document (multi-tenant, modular)

[ ] Define database schema design (Supabase PostgreSQL) communication logs, audit logs, tenants

Users, roles, transactions, tasks, documents, contacts, vendors,

[ ] Design API architecture (RESTful with webhook hooks)

[ ] Set up development environment:

React project scaffolding (Vite + React + TypeScript)

FastAPI project scaffolding (Python)

Supabase project creation (DB + Auth)

AWS EC2 instance provisioning

[ ] Set up CI/CD pipeline (GitHub Actions or similar)

[ ] Set up private Git repository with branching strategy

[ ] Create staging environment on AWS

Success Criteria: Architecture document approved, dev environments operational, CI/CD deploying to staging.

## Milestone 1.2 - Database & Data Model Implementation (Week 2)

STATUS: COMPLETE (schema continues to evolve via migrations; RLS dormant)

Deliverables:

[ ] Implement full database schema in Supabase PostgreSQL: closing date, closing mode, notes, status, use-case type, FSBO state fields) automation level, use-case applicability) related transaction)

Multi-tenant tables with Row Level Security (RLS)

Users, roles, permissions tables

Transactions table (address, representation, price, financing,

Tasks table (name, description, target, dependencies, float,

Documents table (name, type, metadata, version history, soft-delete)

Contacts table (name, email, phone, linked transactions/vendors)

Communication log table (immutable: who, what, when, direction,

Audit log table (user, role, timestamp, action, before/after, message)

Vendor table, advertising hooks table

[ ] Implement database migration scripts

[ ] Import legacy task catalogue (50+ tasks from spreadsheet)

[ ] Set up Supabase storage buckets for documents

[ ] Define and document all API endpoints (OpenAPI/Swagger)

Success Criteria: Database fully operational, task catalogue imported, API documentation available.

## Milestone 1.3 - Authentication & User Management Backend (Week 3)

STATUS: COMPLETE (roles: TransactionCoordinator / ForSaleByOwner, not Elf / FSBO_Customer)

Deliverables:

[ ] Implement Supabase Auth integration (OAuth2/JWT)

[ ] Build registration, login, password reset APIs

[ ] Implement invite-based onboarding flow (token generation + email)

[ ] Build RBAC system: Agent, Elf, Team Lead, Attorney, Admin, Client, FSBO Customer, Vendor

[ ] Implement role-specific permission middleware in FastAPI

[ ] Build contact management API (CRUD for contacts, linking to transactions/vendors)

[ ] Build vendor contact "card" API (additional contacts, opt-in system)

[ ] Implement confidence threshold settings API:

Admin: set global minimum confidence floor

Team Lead: set team thresholds (above admin minimum)

[ ] Unit tests for auth and RBAC

Success Criteria: All 8 roles can register/login, permissions enforced, invite flow working end-to-end.

# Phase 2: Core Transaction & Task Engine

Weeks 4-8 (Mar 30 - May 3)

## Milestone 2.1 - Transaction Management Backend (Week 4)

STATUS: COMPLETE

Deliverables:

[ ] Build transaction CRUD APIs (create, read, update, delete)

[ ] Implement 6 transaction types with validation

[ ] Build transaction assignment API (assign agent/elf/attorney, trigger notifications)

[ ] Implement closing_mode field (attorney closing vs title/escrow vs shared approval) with validation

[ ] Implement FSBO property state support (is_fsbo flag, fsbo_state for listing-prep vs under-contract)

[ ] Build filtered transaction lists per role (sorting, searching, pagination)

[ ] Implement transaction status management (active, incomplete, paused, completed, closed)

[ ] Build transaction type switching logic:

Targeted task updates (not full regeneration)

Task ID comparison for completed status preservation

[ ] Implement export capabilities API (CSV, Excel, PDF generation)

[ ] Build Active Transactions workspace aggregation APIs (per approved Active Transactions redesign): editable key dates)

Topbar AI briefing data (Critical, Needs Attention, On Track)

Sidebar KPI tile data (overdue tasks, closing this week, active deals, pipeline value)

Sidebar Deals counts (Active Transactions, Pending, Closed, All Transactions)

Collapsible transaction card data (status pill, why badges, AI next-step banner, milestone bar, info badges, grouped contacts,

Support personal and team views, deal-state filters, page tabs, urgency sorting, search, and team member filtering

[ ] Build key dates management API (inline edit from expanded drawer): Appraisal Expected, CD Delivered, Cleared to Close, Closing Date (with time-of-day), Possession (with time-of-day)

PUT endpoint for milestone dates: EM Delivered, Inspection Response,

Inline Save/Cancel popover data contract; changes audit-logged

[ ] Build transaction history timeline API: task completions, date changes, and AI flags

Searchable event timeline merging audit logs, communication logs,

Events grouped by date headings (Today, Yesterday, etc.)

Supports search filtering by keyword

[ ] Build workspace AI chat API: transaction_id context response", "Summarize [client] deal"

Contextual AI assistant accepting a message and optional

Returns response and suggested_actions array

Quick-action prompts: "Show overdue tasks", "Draft inspection

[ ] Implement stage pill computation logic:

"Critical", "Needs Attention", "On Track", and "Unhealthy"

"In Inspection" computed when inspection response has not yet been sent

Computed from transaction state, task status, dates, message counts, and missing-document conditions

[ ] Implement pipeline value calculation (sum of active purchase_price)

[ ] Unit and integration tests for transaction APIs

Success Criteria: Full transaction lifecycle operational via API, type switching with targeted updates working, Active Transactions workspace APIs returning correct data, key dates editable via API with audit logging, transaction history timeline and AI chat endpoints operational.

## Milestone 2.2 - Task Engine Backend (Weeks 5-6)

STATUS: COMPLETE (generation + state rules + attorney library; no separate visual rule-builder)

Deliverables:

[ ] Build task CRUD APIs (create, read, update, delete)

[ ] Implement master task library management API (admin-configurable)

[ ] Build dependency engine:

Task-to-task dependencies

Task-to-date dependencies

Float/offset calculations

Rule builder for admin (configure dependencies without code)

[ ] Implement initial task generation logic:

Based on confirmed use case + dates + dependency logic

No AI creativity at generation stage

[ ] Build task template system (per use-case subsets)

[ ] Implement manual task similarity checks:

When creating a task, AI searches for similar incomplete tasks

Present Add / Combine / Disregard choices before save

[ ] Implement task notification engine:

Day-before, due-today, and past-due reminders

Compiled reminder summaries ("X transactions due tomorrow/today")

Configurable reminder intervals

Daily summary email (only when tasks due)

[ ] Build task sorting/views:

By status (previous, today, upcoming)

By vendor ("vendor carts")

Highlight upcoming deadlines

[ ] Implement state-based task rules keyed off closing_mode:

Attorney closing vs title/escrow closing workflows

Recording timelines, disbursement timing

Required attorney involvement in doc prep/settlement

Recording and funding sequence expectations

[ ] Unit and integration tests for task engine

Success Criteria: Tasks auto-generated from use case, dependencies enforced, notifications firing, state-based rules operational.

## Milestone 2.3 - Frontend Foundation & Auth UI (Week 7)

STATUS: COMPLETE

Deliverables:

[ ] Build React app shell matching approved designs (shared across roles): (Dashboard, Deals, Workflow, Intelligence; Team section for Team Lead) user chip, and contextual CTA

Dark sidebar with role-specific KPI tiles and grouped navigation

Slim topbar with brand lockup, AI briefing chip, search, notifications,

Page header + tab bar + scrollable content area

Simplified customer-facing shell variant for FSBO workspace

[ ] Implement brand-aligned design system as CSS variables:

Deep Institutional Navy (#1B2B3C)

Refined Amber Orange (#EE7623)

Soft Cool Grey (#F5F7FA)

Subtle Champagne Glow (#FFEEC2)

Max-Contrast Slate Grey (#333333)

[ ] Implement semantic/functional color tokens as CSS variables: healthy green (#1a7a52), info blue (#2c4c7f), neutral gray (#7a7a7a) briefing badges, and urgency states carry stronger emphasis

Status states: critical red (#c8322f), warning amber (#c07a0a),

Tinted background variants for status pills and badges

Surface tokens: card white, sidebar navy, border grays

AI surfaces use subtle champagne glow accents only

Status pills use tint + border + text for readability; card edge bars,

[ ] Implement login/register/password-reset pages

[ ] Build invite acceptance flow UI

[ ] Implement role-based navigation and access control in React

[ ] Build first-time user overlay tutorial (skippable, re-viewable)

[ ] Add first-upload profile completion prompt

[ ] Create shared UI component library: CD Delivered, CTC, Close)

Collapsible transaction cards with left-edge urgency indicator

AI next-step banners and why badges

Visual milestone timeline (Contract, EM, Inspection, Appraisal,

Page tab bar with live counts (filter tabs and portal tabs)

KPI tiles and AI briefing badges

Grouped contact cards with one-click call/email actions

Command grid layout (hero card + metric cards, fractional widths)

Health score ring (conic-gradient progress indicator)

Upload intake card (drag/drop zone with AI classification)

Portfolio cards (property-centric, for FSBO workspace)

Matter cards (legal review queue, for Attorney workspace)

Data tables with sorting/filtering/pagination

Forms with validation

Modals, notifications, alerts

Responsive layout components

[ ] Apply typography/accessibility rules from the brand kit: role-specific alternates such as DM Sans)

IBM Plex Sans across app UI

IBM Plex Mono for operational values

Limited Lora serif accents for approved brand/display headings only

tabular-nums/lining-nums for dates, money, phones, file IDs, deadlines

6px radius and 48x48 minimum interactive targets

One shared typography system across all roles and portals (no

[ ] Implement white-label theming engine:

Custom logos, colors, themes per tenant

Applied across login, dashboards, email templates

[ ] Connect frontend to Supabase Auth

Success Criteria: Users can register, login, navigate by role (all 8 roles); shared app shell functional (internal + FSBO variant); white-label theming working; shared component library covers command grid, health score, portfolio cards, and matter cards.

## Milestone 2.4 - Transaction & Task UI (Week 8)

STATUS: COMPLETE (list cards + /transactions/:id workspace; attorney matter workspace)

Deliverables:

[ ] Build Agent/Elf Active Transactions workspace per approved redesign: On Track, Unhealthy

Topbar AI briefing row (Today's AI Briefing + status counters)

Sidebar KPI tiles (overdue, closing this week, active deals, pipeline)

Deals / Workflow / Intelligence navigation groups

Page header with count pill, Export CSV, and Print Report

Page tabs: All, Overdue, Due Today, Closing Soon, In Inspection,

[ ] Build collapsible transaction card system: AI next-step banner, primary contact, milestone bar, info badges, days-to-close, overdue count, price, chevron Transaction History, price)

Header: color indicator, name, address, status pill, why badges,

Expanded body: 3-column grid (tasks, key dates, grouped contacts)

AI suggestions strip and footer actions (View/Add Docs, Print Checklist,

[ ] Build page tab bar and sort controls: and addresses

Tabs with live counts

Sort options: Urgency, Close Date, Client Name, Price

Global search across client names, vendor names, companies, dates,

[ ] Build Add Task modal: Upload Document, Online Portal, AI Agent, Other)

Completion methods (Phone Call, Email, E-Sign, In Person,

AI suggestions for how to complete the task

Similar-task Add / Combine / Disregard workflow

[ ] Build document overlays:

Transaction Documents modal (view/add/rename/history)

All Documents AI Search modal across transactions

[ ] Build New Transaction quick-create modal (from topbar and sidebar CTAs): auto-fill all fields") Type (Buyer/Seller/Dual Agency), Purchase Price, Contract Date, Projected Closing Date, Lender/Title Company, Notes

AI Import action ("Paste a contract or MLS listing — AI will

Manual fields: Client Name, Property Address, City/ZIP, Transaction

"Create with AI Checklist" action

[ ] Build Add Contact inline modal: Email Address

Fields: Company Name, First Name, Last Name, Phone Number,

[ ] Build Transaction History panel: Yesterday, etc.) confirmations, and offer events date changes into a unified view

Searchable event timeline organized by date headings (Today,

Shows AI flags, emails received, task completions, date

Merges audit logs, communication logs, task completions, and

[ ] Build floating AI Chat panel ("Velvet Elves AI"): "Summarize Young deal"

Contextual assistant with deal-specific quick-action prompts

Example prompts: "Show overdue tasks", "Draft inspection response",

Supports optional transaction context for scoped assistance

[ ] Build Edit Date popover for inline key-date changes:

Pencil-edit icon on each key date in expanded drawer

Save / Cancel actions with visual urgency states

Overdue dates shown in red

[ ] Build Team Lead adaptation of the Active Transactions workspace:

Team-wide KPI tiles and AI briefing counts

Team member filtering

Assignee names on cards

Team task template access and activity overview

[ ] Build Attorney adaptation of the Active Transactions workspace: Ready To Release, Clean Files active matters, reviewed volume)

Attorney queue filters: All, Needs Review, Missing Docs,

Matter cards with attorney sign-off checkboxes

Legal-specific KPI tiles (hard stops, release-ready packets,

Explicit AI-vs-human boundary in card actions

[ ] Build transaction create/edit forms with validation

Include closing_mode selection (attorney/title-escrow/shared approval)

[ ] Build transaction detail/overview page (full transaction view)

[ ] Build task detail/edit UI

[ ] Build admin task template management UI (edit definitions, dependencies, float, automation flags)

[ ] Build dependency rule builder UI for admins

[ ] Export buttons for transaction lists (CSV, Excel, PDF)

[ ] Integration tests for frontend-backend flows

Success Criteria: Agents/elves can operate from the approved Active Transactions workspace end-to-end including quick-create transactions, inline key-date editing, transaction history, and AI chat; Team Leads can switch to team-scoped transaction views; Attorneys can view and filter their matter queue; admins can configure task templates via UI.

PHASE 2.5: PRE-PHASE 3 DESIGN REVIEW & WORKFLOW LOGIC ALIGNMENT

Week 8.5 (Apr 6 - Apr 13, overlapping with Phase 2 closeout)

## Milestone 2.5 - Frontend UI Workflow Logic Design Review

PURPOSE: Before proceeding to Phase 3 implementation, complete a full design

review pass across all approved designs and requirements to ensure

consistency, identify gaps, and produce a canonical workflow specification

that governs all future frontend implementation.

Deliverables:

[x] Generate complete frontend UI workflow logic specification

(FRONTEND_UI_WORKFLOW_LOGIC.md) covering every route with 10-section

structure: Page Identity & Access, Entry Conditions & Data Loading,

Layout & Component Hierarchy, User Actions & State Transitions,

Conditional Rendering Logic, Navigation Flows, AI Integration Points,

Real-Time & Notification Behavior, Cross-Page Relationships,

Edge Cases & Special Behaviors

[x] Design 12 cross-cutting end-to-end workflows (A–L):

A. New Transaction Creation (quick-create modal + full wizard)

B. Transaction Lifecycle Management (status transitions, type switching)

C. Task Management (generation, manual create, AI intelligence, approval)

D. Document Lifecycle (upload, AI classify, version, email, e-sign)

E. Communication & AI Email (inbound processing, auto-respond, drafts)

F. AI Chatbot Interaction (floating panel, context, quick actions)

G. Attorney Workflow (packet upload, review, release, state rules)

H. FSBO Customer Journey (property-centric, milestones, sharing)

I. Team Lead Workflow (team view, agent board, bulk approval)

J. Notification & Reminder System (in-app, push, email, escalation)

K. Admin Configuration (users, templates, confidence, tenant)

L. Profile & Settings (personal, checklists, integrations)

[x] Define 9 global interaction patterns for consistent cross-page behavior

[x] Update project requirements (requirements.txt) with workflow-derived

additions:

- Transaction status definitions and transitions

- Onboarding wizard steps per role

- Quick-create modal vs full wizard distinction

- Dashboard auto-routing logic

- Client portal and vendor portal page specs

- Public milestone viewer requirements

- Optimistic UI and error handling patterns

- Admin UI requirements (users, templates, confidence, audit, tenant)

- Intelligence section UI requirements (AI suggestions, analytics)

- Deep-linking requirements

[x] Update system design (SYSTEM_DESIGN.md) with new API endpoints:

- AI Suggestions CRUD (/api/v1/ai/suggestions)

- Analytics aggregation (/api/v1/analytics)

- Notifications (/api/v1/notifications)

- Task Queue (/api/v1/tasks/queue)

- Attorney Actions (/api/v1/attorney/approve, release-packet)

- Client Portal (/api/v1/client/*)

- Public Milestone Viewer (/api/v1/milestones/shared/:token)

- Admin endpoints (/api/v1/admin/users, audit-logs)

- Updated permission matrix and frontend state architecture

[x] Update project milestones (milestones.txt) to reference workflow

specification as input to Phase 3+ implementation

[ ] Review 10 approved HTML designs against workflow spec for visual alignment and flag any inconsistencies

[ ] Finalize design review signoff with client

Success Criteria: FRONTEND_UI_WORKFLOW_LOGIC.md approved as the canonical frontend specification; all three project documents (requirements, system design, milestones) updated and internally consistent; no ambiguity remains for Phase 3 frontend implementation.

NOTE: This milestone does not add calendar time to the overall timeline.

It runs during the Phase 2 → Phase 3 transition week and formalizes

design decisions that would otherwise be made ad-hoc during implementation.

# Phase 3: Ai Wizard & Document Management

Weeks 9-13 (May 4 - Jun 7)

NOTE: All Phase 3+ frontend implementation must align with the workflow logic

specification in FRONTEND_UI_WORKFLOW_LOGIC.md, which defines per-page

entry conditions, data requirements, user actions, conditional rendering,

navigation flows, AI integration points, and edge cases.

## Milestone 3.1 - AI Document Parsing Engine (Weeks 9-10)

STATUS: COMPLETE (OpenAI/Claude + Textract; extraction QA continues)

Deliverables:

[ ] Build provider-agnostic AI abstraction layer (OpenAI GPT + Claude) with admin-configurable switching via system settings

[ ] Integrate OpenAI GPT API for document parsing

[ ] Integrate Anthropic Claude API for document parsing

[ ] Build document upload API with format validation (PDF, JPEG, GIF, DOC, DOCX; up to 20 MB)

[ ] Implement auto-compression for files over 10 MB

[ ] Implement multi-page document splitting (page range selection, naming, metadata assignment)

[ ] Build AI extraction pipeline: closing attorney/settlement attorney when present)

Property data extraction (address, city, state, zip)

Transaction data extraction (representation, price, financing, earnest money)

Timeline data extraction (all dates and contingencies)

Party data extraction (buyers, sellers, agents, loan officer, title co.,

Closing mode detection (attorney closing vs title/escrow)

Owner-occupied vs. investor/second home detection

[ ] Implement double-check mechanism:

Two-pass extraction with different prompt strategies

Agreement check on key fields

Confidence scoring per field

Route to human review on disagreement

[ ] Build edge case handling (blurry docs, crooked scans, missing pages)

[ ] Build AI audit logging (document received, extracted, decided, why, human override)

[ ] Unit tests with sample documents

Success Criteria: AI accurately extracts key fields from real estate documents, double-check mechanism functional, confidence scores generated.

## Milestone 3.2 - Wizard UI & Flow (Week 11)

STATUS: COMPLETE (4 public phases, not the original 6-step flow)

Deliverables:

NOTE: Implementation must follow FRONTEND_UI_WORKFLOW_LOGIC.md §4.5 (New

Transaction) and Cross-Cutting Workflow A (New Transaction Creation Flow)

for full action specifications, conditional rendering, and edge cases.

[ ] Build wizard Step 1: Document upload interface (drag-drop, multi-file)

[ ] Add global drag-and-drop upload from anywhere in the authenticated workspace

[ ] Build document preview with splitting UI (page ranges)

[ ] Build wizard Step 2: AI parsing progress/results display

[ ] Build address confirmation screen (normalized, flagged inconsistencies)

[ ] Build purchase information validation screen:

All dates, final price, professional fees

Discrepancy flags with inline alerts

Document preview showing flagged sections

[ ] Build manual entry fallback forms (title company details, etc.)

[ ] Build missing information handling:

Prompt for missing data

AI public source search UI (show search activity)

Results labeled as AI-sourced with confirmation

[ ] Build drag/drop intake confirmation flow:

AI identifies what the document is

Suggests a document name

Confirms which transaction it belongs to

Checks if it needs e-signature handling

[ ] Build wizard confirmation page (all data, edit/accept actions)

[ ] Build "Suggest AI Improvement" button

[ ] Connect wizard to transaction + task generation backend

[ ] End-to-end wizard flow tests

Success Criteria: Complete wizard flow from upload to transaction creation, AI extraction with human verification working.

## Milestone 3.3 - Document Management System (Week 12)

STATUS: COMPLETE

Deliverables:

NOTE: Implementation must follow FRONTEND_UI_WORKFLOW_LOGIC.md §5.3 (All

Documents), §4.6 Transaction Detail Documents tab, and Cross-Cutting

Workflow B (Document Upload & AI Processing) for UI flows and edge cases.

[ ] Build document center UI (upload, view, download, email, archive)

[ ] Build cross-transaction All Documents UI with AI-assisted search

[ ] Implement version history with diffs

[ ] Build vendor document visibility rules (own uploads only, sharing)

[ ] Build attorney document upload support: affidavits, signed amendments, recording packets

Legal packet types: title commitments, settlement statements,

AI-assisted packet indexing, version comparison, exhibit indexing

[ ] Build customer-facing document views (Client and FSBO): Complete

Document status states: Missing, In Progress, Uploaded, Verified,

Role-appropriate actions: Upload New Version, Flag Issue

Shared milestone viewers see read-only status cues only

[ ] Implement soft delete with restore for authorized roles

[ ] Build document emailing UI (recipients, subject, body, attachments, templated emails)

[ ] Implement one-click resend from transaction log

[ ] Build client/FSBO "flag for deletion" feature with agent/elf approval workflow and audit logging

[ ] Implement document metadata management (rename, type assignment)

[ ] Build transaction documents modal flow used by the Active Transactions workspace

[ ] Role-based permissions for all document actions

[ ] Document action audit logging

Success Criteria: Full document lifecycle operational, versioning working, role-based access enforced.

## Milestone 3.4 - E-Signature Integration (Week 13)

STATUS: COMPLETE (DocuSign; HelloSign not wired)

Deliverables:

[ ] Integrate DocuSign API (primary e-sign provider)

[ ] Build e-sign workflow in document center:

Send for signature

Specify recipients for executed copy

Track signature status

Auto-replace original with signed version (old to version history)

Auto-distribute to identified parties

[ ] Build wizard e-sign integration:

Detect unsigned documents during parsing

Offer to send for signature on finalization

Reuse same prompt/decision flow for documents dropped into the workspace

[ ] Implement document naming rules for auto-distribution (PA, C1, Amend -> all parties; other -> agent notification)

[ ] Build prompt for unconnected e-sign users (suggest connecting)

[ ] Integration tests with DocuSign sandbox

Success Criteria: Documents can be sent for e-signature, tracked, returned, versioned, and distributed automatically.

# Phase 4: Communication Engine & Ai Email

Weeks 14-16 (Jun 8 - Jun 28)

NOTE: Communication features must align with FRONTEND_UI_WORKFLOW_LOGIC.md

Cross-Cutting Workflow E (Communication Logging), §5.3 (All Documents),

and §7 (Intelligence Section — AI Settings) for email integration points,

communication log UI, and AI provider configuration.

## Milestone 4.1 - Email Integration (Week 14)

STATUS: COMPLETE (Gmail, Outlook; generic IMAP deferred)

Deliverables:

[ ] Integrate Gmail API (OAuth2 flow, send/receive)

[ ] Integrate Microsoft Graph API for Outlook (OAuth2, send/receive)

[ ] Build email connection flow during account creation

[ ] Define provider-agnostic hooks for future SMS and click-to-call / voice integrations

[ ] Build unified communication log backend:

Immutable log entries (who, what, when, direction, transaction)

Channel support for email now and SMS/voice-ready metadata fields

Search/filtering by date, party, keyword

Indexing for performance

[ ] Implement log download (one transaction at a time per user)

[ ] Build admin export request workflow (multi-transaction)

[ ] Implement 2-year retention with quarterly auto-purge checks

[ ] Build inbound email processing (logging, trigger hooks)

[ ] Unit tests for email integration

Success Criteria: Gmail and Outlook connected, emails sent/received/logged, communication log searchable with retention policy.

## Milestone 4.2 - AI Email Automation (Week 15)

STATUS: COMPLETE (Aime drafts + /ai-emails; autopilot still expanding)

Deliverables:

[ ] Build AI email response engine (OpenAI GPT + Claude via abstraction layer): responsible internal owner, e.g. agent & elf for agent-led files) milestones; always CC the responsible internal owner) with draft; unsure -> notify owner with draft

Auto-respond to vendor/client/FSBO document requests (always CC the

Auto-respond to client/FSBO factual questions (closing date, status,

Apply rules: document exists -> send + CC; missing -> notify owner

[ ] Implement AI draft safeguards:

Detect assumptions/inferences/interpretations

Bold flagged content in draft

"Approve / Edit & Send" button with system link

[ ] Build side-by-side review UI (draft vs. source data with tooltips)

[ ] Implement AI email tone rules (configurable style, no legal advice, uncertainty language, AI disclaimer)

[ ] Build auto-reply feature (AI types response, user modifies or sends)

[ ] Implement in-app notifications for sent external communications

[ ] Build optional escalation reminders (24-48 hours, configurable)

[ ] Build compiled reminder digests for due-today / due-tomorrow transaction deadlines

[ ] AI email audit logging (request, response, confidence, human action)

[ ] Integration tests with email sandbox

Success Criteria: AI responds to routine emails, drafts flagged for review, safeguards prevent unsupervised sending of uncertain content.

## Milestone 4.3 - Vendor Communication System (Week 16)        STATUS: COMPLETE

Deliverables:

[x] Build vendor email templates with constrained response format

("Reply with: Scheduled: YYYY-MM-DD")

→ 5 system templates seeded per tenant via

20260622091000_seed_vendor_email_templates.sql + tenant

provisioning hook. Admin CRUD at /admin/vendor-templates.

[x] Implement AI email reply parsing for vendor responses:

- Extract dates from replies (regex, no extra LLM call)

- Propose task date updates (vendor_proposals table, human-approved)

- Handle vague replies (proposal status='needs_clarification')

→ VendorProposalService.propose_from_vendor_reply invoked from the

AI engine immediately after the vendor_reply draft is persisted.

[x] Build vendor contact card system:

- Public colleague-invite tokens (single-use, SHA-256 hashed, TTL)

- transaction_vendor_assignments + assignment_contacts (one-primary)

- VendorContactCard component with explicit action buttons

[x] Implement saved vendor rep background search (offer updates to info)

→ VendorBackgroundSearchService + vendor_background_refreshes table;

diff drawer with per-field accept/reject.

[x] Document and wire provider-agnostic hooks for future SMS and

click-to-call / voice integrations:

- communication_logs.channel accepts 'sms'/'voice_call' today

- communication_providers.py defines SmsProvider/VoiceProvider protocols

- ChannelBadge renders SMS/Voice "soon" pills; tenant flag

vendor_comms.phone_action_enabled gates click-to-call

[x] Build communication log UI:

- Unified comm-log surface at /admin/communications with filter

row + date grouping (legacy /communications redirects there)

- Per-transaction drawer remains (CommunicationsPanel.tsx)

- Single-transaction CSV via existing /communication-logs/transaction

- Admin multi-tx export at /admin/communication-exports

[x] End-to-end vendor communication flow tests

→ test_vendor_communications_api.py (11 tests passing; 549 backend

tests passing overall).

Success Criteria: Vendor communication automated with structured responses, contact card system operational, communication log complete. Routes added: Backend  /api/v1/vendor-communications/{templates,preview,send, proposals,settings} /api/v1/transactions/{tx}/vendor-assignments[/{id}[/contacts]] /api/v1/vendors/{id}/{colleague-invites,background-refresh, transactions} /api/v1/public/vendor/colleague-invites/{token}[/accept] Frontend /admin/communications (legacy /communications redirects), /vendors, /vendors/:vendorId, /vendor-proposals, /admin/vendor-templates, /v/:token

# Phase 5: Dashboards, Payments & Profiles

Weeks 17-19 (Jun 29 - Jul 19)

NOTE: Dashboard and profile implementations must align with

FRONTEND_UI_WORKFLOW_LOGIC.md §3 (Dashboard Landing Pages), §8 (FSBO

Customer Workspace), §9 (Client Portal), §10 (Admin Section), §11

(Profile), and Cross-Cutting Workflow K (Dashboard Auto-Routing).

## Milestone 5.1 - Role-Specific Dashboards (Week 17)

STATUS: MOSTLY COMPLETE — Agent/Team/Admin/Attorney/Client/Vendor shells

ship; FSBO pages exist and continue to iterate as an operating workspace

Deliverables:

NOTE: Dashboard landing pages are now approved for Solo Agent, Team Leader,

FSBO, and Attorney (approved 2026-03-26). The Active Transactions workspace

was built in Milestone 2.4. This milestone implements the approved dashboard

landing pages plus remaining roles and polish.

[ ] Build Solo Agent Dashboard landing page (per approved design): AI reads docs, builds transaction shell, suggests milestones, identifies missing docs, routes to Active Transactions hero card + production snapshot + transaction overview action queue (ranked transactions needing intervention today), drift diagnostics ("why deals are drifting"), fast filter buttons (critical closings, missing responses, stale communication, document blockers) active transaction counts needed, next-step CTA, key tasks, key dates, contacts, footer actions recent communication highlights shared Active Transactions workspace (no dead-end pages)

Upload intake card: drag/drop or browse zone for document-first intake;

Command grid layout (3-column responsive: 1.55fr / .95fr / .8fr):

Hero card: health score ring (conic gradient, 0-100), health descriptor,

Production snapshot: pending GCI, pending volume, closings YTD/lifetime,

Priority transaction cards: closing soon, in inspection, documents

Side rail: AI portfolio intelligence, missing-doc concentration,

All dashboard cards, fast filters, and AI prompts deep-link into the

[ ] Build Team Leader Dashboard landing page (per approved design): likelihood of breaking, drift/discipline metrics (closings in 7 days with unresolved dependency, no client touch in 72+ hrs, missing signatures/doc gaps, agents needing coaching) agent's book, team financials, pipeline health, annual pace, closings in the next 14 days milestones, recent communication highlights ($79/agent/month) and NOT part of MVP. MVP may preserve architecture hooks or feature-flagged placeholders but should not scope active implementation into the core delivery

Upload intake card (same as Solo Agent)

Command grid layout (same 3-column system):

Hero card: team health score ring, intervention queue ranked by

Team performance modules: agent board with drill-down into individual

Side rail: AI portfolio intelligence, coach prompts, documents blocking

Sidebar Team section: Agents and Task Templates navigation links

NOTE: The AI Coach add-on shown in design files is a future paid feature

[ ] Build Attorney Dashboard landing page (per approved design): statements, affidavits, signed amendments, recording packets; AI extracts deadlines, compares versions, indexes exhibits, flags missing formal docs, routes legal judgment to attorney queue; CTAs: "Open intake" and "Open release queue" matters needing legal judgment, action list of critical approval gates, drift summary (blocked matters, missing formal docs, release-ready packets), filter buttons (needs attorney judgment, missing notarized docs, ready to release, recording/disbursement timing) Clean Files Missing doc), expandable drawer (review queue with sign-off checkboxes, key dates with status colors, AI-prepared next step with context), footer actions (View docs, Audit trail, Send packet, price) timing, same-day release checks, recording calendar, legal/audit quick actions deadlines, index exhibits, draft transmittal language; AI must NOT determine legal equivalence, final packet release, or same-day disbursement exceptions; these remain human-owned

Upload intake card for legal packets: title commitments, settlement

Hero card: legal health score (0-100) focused on approval gates,

Filter tabs: All, Needs Review, Missing Docs, Ready To Release,

Matter card stack: matter name, status pills (Critical, Today,

State rules modal: closing mode, recording timelines, disbursement

Explicit AI-vs-human guardrails: AI may compare versions, extract

[ ] Build FSBO Customer Workspace (per approved design): internal sidebar/topbar) live, missing documents Milestones & Messages, Ask Velvet Elves AI, Notifications, Sharing badges — distinct from filter tabs) title, status pill, portfolio chips (closing date, missing docs, new messages), quick actions (Open timeline, Share link) milestones, current document blockers in plain English, glossary-style explanations viewer-open notifications; shared viewers see timeline and key dates but cannot edit tasks, delete documents, or view internal workflow workflow but does not act as the customer's agent or provide legal advice)

Simplified customer-facing shell (brand-consistent but not the full

Sidebar KPI tiles: critical next steps, days to close, share links

Sidebar navigation: Dashboard, My Properties, Documents,

Portal tabs: Overview, Properties, Documents, Support (with count

Property portfolio strip: portfolio cards per property with property

Support both listing-prep and under-contract property views

Plain-English AI guidance: next decision, why it matters, upcoming

Milestone sharing: read-only milestone links with expiry and

Support/guide contact area with boundary notice (VE coordinates

"Share milestones" primary CTA in topbar

[ ] Build Admin dashboard:

System-wide user management

AI confidence threshold configuration

Task add/remove statistics (global analysis)

System defaults configuration

[ ] Build Client dashboard (milestones, documents, communication)

[ ] Build Vendor dashboard (assigned tasks, document uploads)

[ ] Implement customizable widgets and interactive charts/KPIs

[ ] Build reporting dashboard (in profile):

Task completion rates

Transaction metrics

Search & sort features

Success Criteria: All 8 role dashboards/workspaces functional with real data; Solo Agent, Team Leader, Attorney, and FSBO match approved HTML designs; dashboard cards deep-link into Active Transactions; health score rings, command grids, and portfolio cards rendering; AI-vs-human guardrails enforced on Attorney dashboard.

## Milestone 5.2 - Payment Processing (Week 18)

STATUS: COMPLETE for invoices + $49/deal credit wallet; commission payouts PARKED

Deliverables:

[ ] Integrate Stripe API:

Secure credit-card processing

Transaction fee collection

Commission payouts

[ ] Build invoicing system (create, send, track invoices)

[ ] Build payment tracking UI (payments, refunds, history)

[ ] Implement payment-triggered task/status updates

[ ] Build admin payment access controls (on/off per role)

[ ] Build payment reporting in dashboards

[ ] Implement payment hooks for future accounting integration

[ ] Security testing for payment flows (PCI compliance)

Success Criteria: Agents can collect fees via Stripe, commissions tracked, payment actions trigger task updates.

## Milestone 5.3 - Profiles & Advanced Features (Week 19)

STATUS: COMPLETE (Settings hub + playbook; NLP/feedback depth lighter than original wording)

Deliverables:

[ ] Build brokerage profile (all agents/teams in one dashboard)

[ ] Build agent/team profile:

Internal document center (utility companies by county, etc.)

Preferred vendors management

Buyer and Seller closing checklist templates

Tagged note management for checklist printing

Seller escrow-overage reminder defaults

Closed transaction reminders (tax exemptions, reviews)

Notification preferences (on/off)

[ ] Build client portal:

Milestone sharing

Agent BIO / "Learn About Your Agent"

Notification preferences

[ ] Build FSBO customer portal settings:

Notification preferences management

Milestone sharing preferences (link expiry, viewer alerts)

Support/guide contact preferences

[ ] Build AI closing checklist generator:

Agent sheet and client sheet

Standard data areas per agent/team

Dates, utility info, address change guides

Print action sourced from profile templates

[ ] Implement natural-language task creation:

AI converts plain language to structured task objects

Due date and reminder rule generation

[ ] Build dynamic task intelligence UI:

AI recommendations with reasons/sources

Approve/restore controls

Bulk approval for team leads with preview

[ ] Build task feedback loop UI (post-closing: useful/unnecessary/missing)

Success Criteria: All profile types operational, closing checklists generating, NLP task creation working, AI task recommendations functional.

# Phase 6: White-Label, Integrations & Advertising Hooks

Weeks 20-21 (Jul 20 - Aug 2)

NOTE: White-label and tenant configuration must align with

FRONTEND_UI_WORKFLOW_LOGIC.md §10.8 (Tenant Settings) for branding

configuration UI and §1 (Shared Shell Reference) for theme application

across internal and customer-facing shells.

## Milestone 6.1 - White-Label & Multi-Tenant (Week 20)

STATUS: COMPLETE (branding studio, calendar, CRM webhooks; RLS still dormant)

Deliverables:

[ ] Implement multi-tenant data isolation (Supabase RLS policies)

[ ] Build white-label configuration UI:

Logo upload, brand colors, theme selection

Custom domain/subdomain configuration

[ ] Apply branding across: login, all role-specific dashboards (Solo Agent, Team Leader, Attorney, FSBO), email templates, documents

[ ] Build tenant management admin panel

[ ] Build CRM integration webhooks (generic RESTful endpoints):

Contact sync

Task sync

Two-way data flow architecture

[ ] Build MLO/title company integration hooks

[ ] Implement calendar API integration (Google Calendar, Outlook):

Schedule appointments

Send reminders

Manage events

[ ] Integration tests for multi-tenant isolation

Success Criteria: Multiple tenants with isolated data and custom branding, integration hooks operational and documented.

## Milestone 6.2 - Advertising Hooks & Consumer Site (Week 21)

STATUS: COMPLETE (/advertise storefront + admin/platform ads)

Deliverables:

[ ] Build advertising module architecture hooks:

Modular ad slots in wizard and task screens

Ad format support (banners, text links, sponsored suggestions)

Responsive ad rendering

[ ] Build basic ad management API:

Package creation/pricing

Creative asset upload/approval

Scheduling (where/when ads appear)

Impression/click tracking

[ ] Build basic consumer-facing advertising site:

Landing page

Stripe integration for ad purchases

[ ] Clearly delineate ads from system content

[ ] Ad billing connected to Stripe payment module

[ ] Document advertising API for future expansion

Success Criteria: Ad slot architecture in place, basic ad management working, consumer site live with Stripe.

# Phase 7: Testing, Deployment & Launch

Week 22 (Aug 3 - Aug 9)

NOTE: End-to-end testing must verify all workflows defined in

FRONTEND_UI_WORKFLOW_LOGIC.md Cross-Cutting Workflows A–L, Global

Interaction Patterns 1–9, and Constraints & Rules 1–10. Each page's

edge cases and error states documented in the spec must have test

coverage.

## Milestone 7.1 - Comprehensive Testing & Hardening (Week 22 - First Half)

STATUS: PARTIAL — large unit/integration + Chrome QA packs; Aime/task-library

cutover still client-tested on staging as of 2026-08-25

Deliverables:

[ ] Complete unit test coverage for all modules (>80%)

[ ] Run full integration test suite

[ ] End-to-end testing of critical flows: state rules, AI-vs-human guardrails enforced) sharing with expirable links, plain-English AI guidance)

User registration/login (all 8 roles)

Full wizard flow (upload -> parse -> confirm -> transaction)

Task generation and dependency enforcement

Document upload/version/email/e-sign

AI email automation with safeguards

Payment processing

White-label tenant isolation

Solo Agent dashboard (intake, health score, deep-link to transactions)

Team Leader dashboard (team metrics, intervention queue, agent drill-down)

Attorney dashboard (matter queue, packet upload, release approval,

FSBO workspace (property portfolio, document submission, milestone

Dashboard-to-Active-Transactions deep-link flow

[ ] Security audit:

OWASP Top 10 checks

PII encryption verification (at rest and in transit)

RBAC permission enforcement testing (all 8 roles)

Attorney AI guardrail testing (legal judgment not delegated to AI)

Payment security (PCI compliance)

[ ] Performance testing (load testing for concurrent users)

[ ] WCAG AA accessibility audit

[ ] Fix all critical and high-severity bugs

Success Criteria: All critical flows passing, security audit clean, performance acceptable, accessibility compliant.

## Milestone 7.2 - Production Deployment & Handoff (Week 22 - Second Half)

STATUS: PARTIAL — prod ECS/Supabase/domains live; client QA on staging;

training/handoff not closed

Deliverables:

[ ] Configure production AWS EC2 environment

[ ] Set up production Supabase instance with backups

[ ] Implement backup strategy and disaster recovery plan

[ ] Deploy application to production via CI/CD

[ ] Configure custom domain and SSL certificates

[ ] Verify all integrations in production:

Email (Gmail, Outlook)

E-signature (DocuSign)

Payments (Stripe)

AI APIs (OpenAI + Claude)

[ ] Deliver technical documentation:

API documentation (Swagger/OpenAPI)

Architecture diagrams

Deployment runbook

Database schema documentation

[ ] Deliver user training materials

[ ] Deliver deployment scripts and configuration docs

[ ] Final source code transfer to client private repository

[ ] Establish post-launch support agreement (optional)

Success Criteria: Application live in production, all documentation delivered, source code transferred, support agreement in place.

# Key Dependencies & Risks

1. Task Spreadsheet Delivery: Client must provide REWORKING TASK DB.xlsx

by Week 2 for task catalogue import.

2. API Credentials: Gmail, Outlook, DocuSign, Stripe, OpenAI, and

Anthropic (Claude) API credentials/accounts must be available by

Week 9 (AI), Week 13 (e-sign), Week 14 (email), Week 18 (payments).

3. Legacy Codebase Access: Access to current ASP.NET MVC codebase needed

by Week 1 for review.

4. Client Feedback Loops: Wizard flow (Week 11) requires client review and

approval within 2-3 business days to avoid timeline slippage.

NOTE: Active Transactions page design approved by client (2026-03-19) and

moved into Week 8 implementation. Dashboard landing pages for Solo Agent,

Team Leader, Attorney, and FSBO approved by client (2026-03-26) and

incorporated into Milestone 5.1 deliverables. Active Transactions UI

alignment (key dates, modals, transaction history, AI chat) finalized

2026-03-30 and incorporated into Milestones 2.1 and 2.4.

5. Third-Party API Limitations: E-signature provider sandbox

availability and email provider OAuth approval processes may

introduce delays. MLS feed integration has been deferred from

the MVP (transaction details are populated from user-uploaded

documents instead).

6. Scope Creep: The advertising module, consumer-facing site, and some

advanced AI features (NLP task creation, predictive analytics) are

scoped minimally for MVP. Expanding these risks timeline overrun.

7. AI Coach Feature: The AI Coach add-on shown in Team Leader design files

is a future paid feature ($79/agent/month) and NOT part of MVP. MVP may

preserve architecture hooks or feature-flagged placeholders but should not

scope active implementation into the core delivery.

8. Attorney AI Guardrails: Attorney dashboard implementation must enforce

explicit boundaries between AI-prepared work and human legal judgment.

Final legal position, packet release approval, and same-day disbursement

exceptions remain human-owned. Testing must verify these guardrails.

POST-MVP ROADMAP (still not in the shipping product)

- Native/hybrid mobile app

- Generic IMAP/SMTP email fallback

- Specific CRM integrations (Follow Up Boss, etc.) — generic webhooks only

- Advanced predictive analytics beyond current drift diagnostics

- AI custom video creator for milestones

- "Orphan Accounts" marketing dashboard

- Expanded SMS / click-to-call (data model ready; Twilio not wired)

- Full advertising platform build-out beyond current storefront

- Pattern detection across teams

- Role-specific Active Transactions pages beyond the shared list + workspace

- AI Coach paid add-on ($79/agent/month) — locked teaser only

- Concierge / Concierge-Style upsell (distinct from Client portal branding)

- "Active Listings" deal-state navigation item

- Commission / Stripe Connect payouts (parked)

- FSBO self-listing (after v1)

- Supabase RLS activation for client-direct access